## Sheet1
Task | Sprint | Points Left | Points
Make Burndown Chart | 5 | 530 | 10
Create UI System | 6 | 520 | 30
Finish Particles | 6 | 490 | 20
Create Game Project | 6 | 470 | 10
Improve Particle System | 7 | 460 | 40
Implement Image Buttons | 7 | 420 | 20
Make Profiling Document | 7 | 400 | 10
Finish Particle System | 8 | 390 | 10
Improve Audio | 9 | 380 | 10
Link Image Buttons to Functions | 10 | 370 | 15
Implement Physics | 10 | 355 | 40
Create Particle Editor | 11 | 315 | 30
Implement Model Loader | 12 | 285 | 50
Convert FMOD to a System | 12 | 235 | 10
Implement function passing for button clicking | 13 | 225 | 10
Add UI to Particle Editor | 13 | 215 | 10
Create UI System | 13 | 205 | 10
Improve Particle Editor Architecture | 13 | 195 | 10
Implement Particle Saving & Loading | 14 | 185 | 20
Add the Model Component | 16 | 165 | 25
Improve React Physics System | 17 | 140 | 20
Add /assets string to the Particle Editor filepath | 17 | 120 | 10
Load Images for UI Library | 18 | 110 | 10
Add Button Anchoring to UI Library | 18 | 100 | 10
Add Gravity and Drag to Particle System | 18 | 90 | 10
Create Sandbox Scene to show off project | 18 | 80 | 10
Add Sphere Component to Physics | 18 | 70 | 10
Comment everything | 19 | 60 | 20
Fully Implement the UI System | 19 | 40 | 40
Project Complete | 20 | 0 | 0