## Sheet1
Sprint # | Sprint Date | Task | Members | Minutes
1 | 13/01/2020 - 16/01/2020 | Research Model Loading | Nabil Salim | 30
|  | Ask Simon about using Box2D, a UI library & Audio API | Spencer Deane | 5
2 | 16/01/2020 - 23/01/2020 | Clean up the engine code | George Hanks | 60
|  | Implement a profiler | Spencer Deane | 45
|  | Create 3D Model Tanks | Jarrad Morden | 40
|  | Implement namespaces | James Dixon | 90
|  | Implement Uniform Buffers & Rendering additions | George Hanks | 120
|  | Re-structure the file system | Jarrad Morden | 90
|  | Decide which 3D Physics Engine to use | George Hanks | 15
|  | Pick & Research Individual Task | Nabil Salim, Spencer Deane, Jarrad Morden, George Hanks, James Dixon | 60
|  | Begin the Games Design Documentation | Jarrad Morden | 120
3 | 23/01/2020 - 06/02/2020 | Implement ImGUI | Spencer Deane | 120
|  | Research Physics Engine | James Dixon | 45
|  | Partially Implement Physics Engine | James Dixon, George Hanks | 360
4 | 06/02/2020 - 13/01/2020 | Renderer Improvements (Geometry and Tesselation shading) | George Hanks | 120
|  | Flesh out the games design documentation | Jarrad Morden | 30
5 | 13/02/2020 - 20/02/2020 | Lay foundations for particle system | George Hanks | 60
|  | Added Renderer Improvements | George Hanks | 40
|  | Implemented Audio | Spencer Deane | 90
6 | 20/02/2020 - 05/03/2020 | Create UI System | Spencer Deane | 60
|  | Finish Particles | George Hanks | 30
|  | Create Game Project With Camera, Plane & Tiled Texture | Jarrad Morden | 20
7 | 05/03/2020 - 12/03/2020 | Improve Particle System | George Hanks | 30
|  | Implement Image Buttons | Spencer Deane | 30
|  | Make Document showing profiling data | Spencer Deane | 40
8 | 12/03/2020 - 19/03/2020 | Finish Particle System | George Hanks | 40
9 | 19/03/2020 - 21/03/2020 | Audio Improvements | Spencer Deane | 40
10 | 21/03/2020 - 25/03/2020 | Link Image Buttons to Functions | Spencer Deane | 60
|  | Implement React Physics | James Dixon | 100
11 | 25/03/2020 - 29/03/2020 | Create Particle Editor | George Hanks | 110
12 | 29/03/2020 - 05/04/2020 | Implement Model Loader | Nabil Salam, George Hanks | 500
|  | Make FMOD a system | Spencer Deane | 15
13 | 05/04/2020 - 10/04/2020 | Implement non-static function passing for button clicking | Spencer Deane | 50
|  | Add ImGui buttons to the Particle Editor | George Hanks | 30
|  | Create the UI System | Jarrad Morden | 50
|  | Improve Particle Editor Architecture | George Hanks | 40
14 | 10/04/2020 - 17/04/2020 | Make Burndown Chart | Spencer Deane | 30
|  | Implement Particle Saving and Loading | Spencer Deane | 60
15 | 25/04/2020 - 02/05/2020 | Add the Model Component | James Dixon | 90
16 | 02/05/2020 - 10/05/2020 | Improve React Physics System | James Dixon | 120
|  | Add /assets string to start of Particle Editor filepath | Spencer Deane | 20
17 | 10/05/2020 - 18/05/2020 | Load Images for UI Library | Jarrad Morden | 50
|  | Add Button Anchoring to UI Library | Spencer Deane | 30
|  | Add Gravity and Drag to Particle System | George Hanks | 50
|  | Create Sandbox Scene to show off project | James Dixon, George Hanks | 50
|  | Add Sphere Component to Physics | James Dixon | 60
18 | 18/05/2020 - 23/05/2020 | Comment Everything | Spencer Deane, George Hanks, Jarrad Morden, Nabil Salam | 40 | Total Hours: | 56.4167