## Sheet1
Sprint | Task | Members | Minutes
13/01/2020 - 16/01/2020 | Research Model Loading | Nabil Salim | 30
| Ask Simon about using Box2D, a UI library & Audio API | Spencer Deane | 5
16/01/2020 - 23/01/2020 | Clean up the engine code | George Hanks | 60
| Implement a profiler | Spencer Deane | 45
| Create 3D Model Tanks | Jarrad Morden | 90
| Implement namespaces | James Dixon | 90
| Implement Uniform Buffers & Rendering additions | George Hanks | 120
| Re-structure the file system | Jarrad Morden | 90
| Decide which 3D Physics Engine to use | George Hanks | 30
| Pick & Research Individual Task | Nabil Salim, Spencer Deane, Jarrad Morden, George Hanks, James Dixon | 60
| Begin the Games Design Documentation | Jarrad Morden | 120
23/01/2020 - 06/02/2020 | Implement ImGUI | Spencer Deane | 60
| Research Physics Engine | James Dixon | 45
| Partially Implement Physics Engine | James Dixon, George Hanks | 360
06/02/2020 - 13/01/2020 | Renderer Improvements (Geometry and Tesselation shading) | George Hanks | 120
| Flesh out the games design documentation | Jarrad Morden | 30
13/02/2020 - 20/02/2020